## 2020 complete
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF THE INTERNAL REVENUE ALLOTMENT (IRA)
AS OF THE 2nd QUARTER, CY 2020(as of June 30, 2020)
Province: BOHOL
| Program or Project |  |  | Location | Total Cost | Date Started | Target Completion | Project Status |  | No. of Extensions if any | Remarks (Status of implementation)
[8 empty] | % of Completion | Total Cost incurred to Date
GENERAL SERVICES
| 1 | Loan Amortization (For Hospital Modernization Program Phase 1) |  | 10 Devolved Hospitals | 14112637.78 |  | Dec. 31, 2020 | 56.88% | 8026429.1 |  | Loan Amortization (with interest) for Hospital Modernazation (1st phase) due as of June 30, 2020 per schedule
| 2 | Loan Amortization (ForNew Loans)
|  | 2.1 | Hospital Modernanzation Phase 2 (est. P195.168 million) |  | 7806720 | [5 empty] | Identified as sources for realignment of appropriation to Supplemental Budget intended for CoVID-19 Response; Related loan stll in application phase as of June 30, 2020.
|  | 2.2 | Hospital Modernanzation Phase 3 (est. P265 million) |  | 10600000
|  | 2.3 | Heavy equipment Loan (est. P218million) |  | 8720000
|  | Sub-Total |  |  | 41239357.78 |  |  |  | 8026429.1
ECONOMIC SERVICES
| 3 | Provincial Roads/ Roads Development and Rehabilitation Program | [9 empty] | PEO
|  | 3.1 | Improvement/Upgrading of LaPaz (Cortes)-Cabaguan-Lourdes-CorellaRoad | Cortes & Corella | 15000000 | [5 empty] | DED On-going | PEO
|  | 3.2 | Improvement/Upgrading of Corella-Balilihan Road | Corella & Balilihan | 15000000 | [5 empty] | DED On-going | PEO
|  | 3.3 | Improvement/Upgrading of Poblacion(Catigbian)-Rizal-Causwagan Sur (San Isidro) Road | Catigbi-an & San Isidro | 10000000 | [5 empty] | Obligated/For Bidding | PEO
|  | 3.4 | Improvement/Upgrading of Pondol – Pananquilon – Catam-is Road, Loon | Loon | 4500000 | [5 empty] | Obligated/For Bidding | PEO
|  | 3.5 | Improvement/Upgrading of Poblacion (Catigbian) – Ambuan – Sagasa (Balilihan) Road | Balilihan & Catigbian | 4500000 | [5 empty] | Obligated/For Bidding | PEO
|  | 3.6 | Improvement/Upgrading of Jct. (LIR) San Miguel–Bayongan–Bulilis–Mabuhay(Ubay) Road | San Miguel & Ubay | 40000000 | [5 empty] | Obligated/For Bidding | PEO
|  | 3.7 | Improvement/Upgrading of Jct. (LIR) Mahayag-Danao Road | Danao | 9500000 | [5 empty] | DED On-going | PEO
|  | 3.8 | Improvement/Upgrading of Poblacion (Sagbayan) – Sagbayan Sur – Kabasakan Road | Sagbayan | 9500000 | [5 empty] | Obligated/For Bidding | PEO
|  | 3.9 | Improvement/Upgrading of Bogtong-Lapacan (Inabanga) – Magkaya – Panghagban (Buenavista) Road | Inabanga & Buenavista | 9500000 | [5 empty] | Obligated/For Bidding | PEO
|  | 3.10 | Improvement/Upgrading of San Miguel – Tomoc – Getafe Road, Getafe side | San Miguel & Getafe | 9500000 | [5 empty] | DED On-going | PEO
|  | 3.11 | Improvement/Upgrading of Poblacion Inabanga – Lawis Road | Inabanga | 8000000 | [5 empty] | Obligated/For Bidding | PEO
|  | 3.12 | Improvement/Upgrading of Cabantian – Cansiwang – Mayuga Road, Guindulman | Guindulman | 18000000 | [5 empty] | DED On-going | PEO
|  | 3.13 | Improvement/Upgrading of Poblacion (Sierra Bullones) – Bugsok Road, Sierra Bullones | Sierra Bullones | 8000000 | [5 empty] | Obligated/For Bidding | PEO
|  | 3.14 | Improvement/Upgrading of Tiguis-Calvario (Lila) – Cambanse – Alegria (Loboc) Road, Loboc | Lila & Loboc | 30000000 | [5 empty] | DED On-going | PEO
|  | 3.15 | Improvement/Upgrading of Bagumbayan – Inaghuban Road, Pilar | Pilar | 8000000 | [5 empty] | Obligated/For Bidding | PEO
|  | 3.16 | Concreting/Improvement of Pitogo – Aguining Road, Pres. Carlos P. Garcia | Pres. C.P. Garcia | 5000000 | [5 empty] | Obligated/For Bidding | PEO
|  | 3.17 | Rehabilitation of Buenavista Circumferential Road (Asinan Road at Barangay Asinan, Buenavista) | Buenavista | 3280000 | [5 empty] | Obligated/For Bidding
| 4 | Water Development Projects for Local Governments (@ P 1.0 million/LGU) |  | Provincewide | 48000000 | [5 empty] | No disbursement in the form of financial assistance to LGUs; pending submission of LGUs' proposed program of works (POW).
| 5 | Wareworks/Water/ Irrigation Development Program |  | Provincewide | 10000000 | [5 empty] | Two (2) Purchase request for water geo-resistivity/drip irrigation project with ABCs at P5 million each earmarked on January 30 and February 7, 2020
50 | 6 | Water Desalination Project |  |  | 6500000 | [5 empty] | No PR submitted for this project as of March 31, 2020; Implementation subject to completion and assessment of a prior implemented similar project (Island barangay in Getafe) | PEO
| 7 | Improvement/Rehabilitation/Establishment of Markets |  | Provincewide | 10000000 | [5 empty] | No PR submitted for this project as of March 31, 2020; Identified as sources for realignment of appropriation to Supplemental Budget intended for CoVID-19 Response
| 8 | Construction of Manpower Development Center/Innovation Hub |  | Tagbilaran City | 20000000 | [5 empty] | No PR submitted for this project as of March 31, 2020; Identified as sources for realignment of appropriation to Supplemental Budget intended for CoVID-19 Response
| 9 | Provincial Counterpart for the establishment of the Integrated Coconut Processing Hub |  |  | 15000000 | [5 empty] | Proposed not yet approved due to realignment of funds in relation to COVID 19
| 10 | Capital Expenditures for the Establishment of Provincial Plant Nursery at Calatrava, Carmen, Bohol |  | Carmen | 1230000 | [5 empty] | Pending meeting with DAR due to COVID 19 re: Reconciliation on lot donation on the proposed project site
| 11 | Mangrove Plantation Project of Selected Coastal Island Barangays of Local Government Units |  | Provincewide | 2000000 | [5 empty] | For bidding May 20, 2020
| 12 | Milk Fish Nursery Center |  | Provincewide | 1036560 | [5 empty] | For bidding
| 13 | Capital Investment in the Establishment and Operation of Eight (8) Seaweeds Nursery Sites Managed by People Organization |  | Provincewide | 2000000 | [5 empty] | For bidding May 20, 2020
| 14 | Capital Expenditures for the Establishment of Bangus Fingerlings Production and Holding Area (3 sites) |  | Provincewide | 9300000 | [5 empty] | MAO was finalized subject to deliberation by the Board of Regents of BISU
| 15 | Capital Expenditures for the Agri-Fishery Development Program through the Establishment of Nurseries, Hatcheries, Seaweeds, Production Areas |  | Provincewide | 10000000 | [5 empty] | Revision amnd finalization of POWs, PR preparation For revision of POW to respond to the need of PO affected by COVID 19
| 16 | Provincial Farm Machinery Facilities |  | Provincewide | 12000000 | [5 empty] | Farm machineries awarded to supplier
| 17 | Establishment of Small-Scale Rice Processing System for High Quality Post-Harvest Processing |  | Provincewide | 12500000 | [5 empty] | Equipments awarded to supplier
| 18 | Establishment of Checkdams as soil and water conservation structures |  | Provincewide | 10000000 | [5 empty] | Revision and finalization of POWs, design, bill of materials
| 19 | Provincial Counterpart for the Implementation of the Philippine Rural Development Program (PRDP) |  | Provincewide | 20000000 | [5 empty] | Transferred to PRDP Trust Fund as Provincial Counterpart to PRDP Sub-projects
| 20 | Establishment of Slaughterhouses in Strategic Areas of the Province |  | Provincewide | 5000000 | [5 empty] | Approved Work and Financial Plan
| 21 | Capital Expenditures in support to the Dairy Development Program |  | Provincewide | 3000000 | [5 empty] | Work and Financial Plan for approval
| 22 | 3. Capital Expenditures in support to the Bohol Livestock and Poultry Production (Establishment of swine semen processing center, Asolla Greenhouse Unit, Swine Building, Forage Nursery Greenhouse) |  | Provincewide | 2000000 | [5 empty] | Approved Work and Financial Plan, Approved PPMP, Program of Work for approval
| 23 | Capital Expenditures for Native Chicken Program |  | Provincewide | 500000 | [5 empty] | Approved Work and Financial Plan,Approved PPMP
| 24 | Reforestation Program |  | Provincewide | 2954223.02
|  | Sub-Total |  |  | 410300783.02 |  |  |  | 0
|  | TOTAL |  |  | 451540140.8 |  |  |  | 8026429.1
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
| JOSETH J. CELOCIA |  |  |  | JOHN TITUS J. VISTAL |  |  |  | ARTHUR C. YAP
| Provincial Accountant |  |  | Provincial Planning and Development Coordinator |  |  |  |  | Governor

## GO (hidden)
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF THE INTERNAL REVENUE ALLOTMENT (IRA)
AS OF THE 1St QUARTER, CY 2018 (as of March 31, 2018)
Province: BOHOL
Office: Office of the Governor
Program or Project |  | Location | Total Cost | Date Started | Target Completion | Project Status |  | No. of Extensions if any | Remarks (Status of implementation)
[6 empty] | % of Completion | Total Cost incurred to Date
GENERAL SERVICES
1 | Loan Amortization (For Hospital Modernization Program Phase 1) |  | 22475000 | [6 empty] | GO
| Sub-Total |  | 22475000
ECONOMIC SERVICES
12 | Roads Development Program for Bohol LGUs |  | 8000000 | [6 empty] | GO
13 | Waterworks Program for Bohol LGUs |  | 3000000 | [6 empty] | GO
14 | Electrification Program for Bohol LGUs |  | 1500000 | [6 empty] | GO
15 | Various Infrastructure Projects for Bohol LGUs |  | 15000000 | [6 empty] | GO
| Sub-Total |  | 27500000
| TOTAL |  | 49975000
Prepared by:

## BDJ (hidden)
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF THE INTERNAL REVENUE ALLOTMENT (IRA)
AS OF THE 1St QUARTER, CY 2018 (as of March 31, 2018)
Province: BOHOL
Office: Bohol District Jail (BDJ)
Program or Project |  | Location | Total Cost | Date Started | Target Completion | Project Status |  | No. of Extensions if any | Remarks (Status of implementation)
[6 empty] | % of Completion | Total Cost incurred to Date
GENERAL SERVICES
2 | Water Supply Development at the Bohol District Jail (2 Water Tanks) |  | 150000 | [6 empty] | BDJ
3 | Construction of no contact visiting building |  | 1000000 | [6 empty] | BDJ
4 | Construction of 2 cells for mentally-ill inmates |  | 700000 | [6 empty] | BDJ
| Sub-Total |  | 1850000
| TOTAL |  | 1850000
Prepared by:

## PEO (hidden)
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF THE INTERNAL REVENUE ALLOTMENT (IRA)
AS OF THE 1St QUARTER, CY 2018 (as of March 31, 2018)
Province: BOHOL
Office: Provincial Engineer's Office (PEO)
| Program or Project |  |  | Location | Total Cost | Date Started | Target Completion | Project Status |  | No. of Extensions if any | Remarks (Status of implementation)
[8 empty] | % of Completion | Total Cost incurred to Date
ECONOMIC SERVICES
| 5 | Provincial Roads/ Roads Development and Rehabilitation Program | [9 empty] | PEO
|  | 5.1 | Concreting of Cabad Road, Balilihan |  | 5000000 | [6 empty] | PEO | PEO
|  | 5.2 | Concreting of Catigbian - Ambuan - Sagasa Road |  | 5000000 | [6 empty] | PEO | PEO
|  | 5.3 | Concreting of Baclayon - Corella Road |  | 3500000 | [6 empty] | PEO | PEO
|  | 5.4 | Concreting of Cahayag (Tubigon) Causwagan Sur (San Isidro) Road |  | 5000000 | [6 empty] | PEO | PEO
|  | 5.5 | Concreting of Baclayon - Corella Via Tunga Road |  | 2000000 | [6 empty] | PEO | PEO
|  | 5.6 | Concreting of Oneway Traffic, Inabanga |  | 5000000 | [6 empty] | PEO | PEO
|  | 5.7 | Concreting of San Miguel - Tomoc - Jetafe Road (San Miguel Side) |  | 5000000 | [6 empty] | PEO | PEO
|  | 5.8 | Concreting of Casbu Circumferential Road, Guindulman |  | 5000000 | [6 empty] | PEO | PEO
|  | 5.9 | Upgrading of San Isidro, Balilihan Road |  | 3633496.4 | [6 empty] | PEO | PEO
|  | 5.1 | Concreting of Maribojoc-Antequera-via Tinibgan Road |  | 4000000 | [6 empty] | PEO | PEO
|  | 5.11 | Concreting of Guinsularan - Lobogon Road, Duero |  | 4000000 | [6 empty] | PEO | PEO
|  | 5.12 | Concreting of Popoo - Tugas Road CPG |  | 5000000 | [6 empty] | PEO | PEO
|  | 5.13 | Concreting of Batuan - Quezon Road |  | 5000000 | [6 empty] | PEO | PEO
|  | 5.14 | Widening and Upgrading of New Capitol Heights Road |  | 15000000 | [6 empty] | PEO | PEO
|  | 5.15 | Upgrading of Mayacabac-Poblacion, Dauis Road |  | 20000000 | [6 empty] | PEO | PEO
|  | 5.16 | Concreting of Right of Way of the new Cong. Natalio P. Castillo, Sr. Memorial Hospital, Loon |  | 2000000 | [6 empty] | PEO | PEO
|  | 5.17 | Development of Public Access Road along New Provincial Compound, Tagbilaran City |  | 8000000 | [7 empty] | PEO
|  | 5.18 | Concreting of Road at Uptown Housing, Tagbilaran City |  | 5000000 | [7 empty] | PEO
|  | 5.19 | Concreting of Sikatuna-Balilihan Road Via Can-agong/ Poblacion 2 (Sikatuna) |  | 5000000 | [7 empty] | PEO
|  | 5.2 | Construction of Access Road to PGBh Property in Cortes |  | 5000000 | [7 empty] | PEO
| 6 | Lot Acquisition (Right of Way for Hangos Street) Additional (c/o PEO, PLO, PGSO) |  |  | 22500000 | [7 empty] | PEO | In Collaboration with PGSO and PLO
| 7 | Construction of foot bridge at Loreto , Cortes |  |  | 6000000 | [7 empty] | PEO
50 | 8 | Construction of New MQC Building of PEO |  |  | 4000000 | [6 empty] | PEO | PEO
| 9 | Waste Water treatment facility at new Capitol Compound to promote water quality (In Collaboration with PGSO) |  |  | 16500000 | [7 empty] | PEO | In Collaboration with PGSO
| 10 | Construction of the Provincial Manpower Development Center at the New Capitol Heights Compound |  |  | 10000000 | [7 empty] | PEO
| 11 | Road Network Development and other related infrastructure at Bohol Biodiversity Complex, BBC (Phase 1) – Roxas, Bilar, Bohol (c/o PEO and PEEMU) |  |  | 2000000 | [7 empty] | PEO | In Collaboration with PEEMU
|  | Sub-Total |  |  | 178133496.4
SOCIAL SERVICES
| 29 | Construction of the Bohol Youth Home (c/o PEO and OPSWD) |  |  | 80000000 | [6 empty] | Candijay Community Hospital - Candijay | PEO AND OPSWD
|  | Sub-Total |  |  | 80000000
|  | TOTAL |  |  | 258133496.4
Prepared by:

## PGSO (hidden)
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF THE INTERNAL REVENUE ALLOTMENT (IRA)
AS OF THE 1St QUARTER, CY 2018 (as of March 31, 2018)
Province: BOHOL
Office: Provincial General Services Office (PGSO)
Program or Project |  | Location | Total Cost | Date Started | Target Completion | Project Status |  | No. of Extensions if any | Remarks (Status of implementation)
[6 empty] | % of Completion | Total Cost incurred to Date
ECONOMIC SERVICES
6 | Lot Acquisition (Right of Way for Hangos Street) Additional (c/o PEO, PLO, PGSO) |  | 22500000 | [6 empty] | PEO | In Collaboration with PGSO and PLO
9 | Waste Water treatment facility at new Capitol Compound to promote water quality (c/o PEO and PGSO) |  | 16500000 | [6 empty] | PEO | In Collaboration with PGSO
16 | Improvement / Construction / Rehabilitation of PGBh Facilities / Cultural Assets/ Designated Evacuation Center for Public Use to Support Development |  | 16200000 | [6 empty] | PGSO
| TOTAL |  | 55200000
Prepared by:

## PLO (hidden)
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF THE INTERNAL REVENUE ALLOTMENT (IRA)
AS OF THE 1St QUARTER, CY 2018 (as of March 31, 2018)
Province: BOHOL
Office: Provincial Legal Office (PLO)
Program or Project |  | Location | Total Cost | Date Started | Target Completion | Project Status |  | No. of Extensions if any | Remarks (Status of implementation)
[6 empty] | % of Completion | Total Cost incurred to Date
ECONOMIC SERVICES
6 | Lot Acquisition (Right of Way for Hangos Street) Additional (c/o PEO, PLO, PGSO) |  | 22500000 | [6 empty] | PEO | In Collaboration with PGSO and PLO
| TOTAL |  | 22500000
Prepared by:

## OPA (hidden)
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF THE INTERNAL REVENUE ALLOTMENT (IRA)
AS OF THE 1St QUARTER, CY 2018 (as of March 31, 2018)
Province: BOHOL
Office: Office of the Provincial Agriculturist (OPA)
Program or Project |  | Location | Total Cost | Date Started | Target Completion | Project Status |  | No. of Extensions if any | Remarks (Status of implementation)
[6 empty] | % of Completion | Total Cost incurred to Date
ECONOMIC SERVICES
17 | On-farm rice mechanization and postharvest facilities to rainfed areas |  | 5000000 | [6 empty] | OPA
18 | Fish Bagsakan Program - Purchase of 1 Unit Ice Maker |  | 1200000 | [6 empty] | OPA
19 | Fish Bagsakan Program - Construction of Fish Bagsakan Building and Display Racks |  | 2300000 | [6 empty] | OPA
| TOTAL |  | 8500000
Prepared by:

## OPV (hidden)
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF THE INTERNAL REVENUE ALLOTMENT (IRA)
AS OF THE 1St QUARTER, CY 2018 (as of March 31, 2018)
Province: BOHOL
Office: Office of the Provincial Veterinarian (OPV)
Program or Project |  | Location | Total Cost | Date Started | Target Completion | Project Status |  | No. of Extensions if any | Remarks (Status of implementation)
[6 empty] | % of Completion | Total Cost incurred to Date
ECONOMIC SERVICES
21 | Provincial Meat Safety and Control Program (Capital expenditure Component) - Upgrading of Slaughterhouses |  | 2000000 | [6 empty] | OPV
22 | Livestock Production Support Program (Capital expenditure Component) Provision of support to liquid nitrogen plant |  | 1500000 | [6 empty] | OPV
23 | Provincial Livestock and Poultry Farm |  | 2000000 | [6 empty] | OPV
| Sub-Total |  | 5500000
| TOTAL |  | 5500000
Prepared by:

## BEMO (hidden)
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF THE INTERNAL REVENUE ALLOTMENT (IRA)
AS OF THE 1St QUARTER, CY 2018 (as of March 31, 2018)
Province: BOHOL
Office: Bohol Environment Management Office (BEMO)
Program or Project |  | Location | Total Cost | Date Started | Target Completion | Project Status |  | No. of Extensions if any | Remarks (Status of implementation)
[6 empty] | % of Completion | Total Cost incurred to Date
ECONOMIC SERVICES
24 | Construction of native cottages for local and foreign researchers, students, volunteers, and walk-in visitors at the Bohol Biodiversity Center |  | 1000000 | [6 empty] | BEMO
| Sub-Total |  | 1000000
| TOTAL |  | 1000000
Prepared by:

## PEEMU (hidden)
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF THE INTERNAL REVENUE ALLOTMENT (IRA)
AS OF THE 1St QUARTER, CY 2018 (as of March 31, 2018)
Province: BOHOL
Office: Provincail Economic Enterprise Management Unit (PEEMU)
Program or Project |  | Location | Total Cost | Date Started | Target Completion | Project Status |  | No. of Extensions if any | Remarks (Status of implementation)
[6 empty] | % of Completion | Total Cost incurred to Date
ECONOMIC SERVICES
11 | Road Network Development and other related infrastructure at Bohol Biodiversity Complex, BBC (Phase 1) – Roxas, Bilar, Bohol (c/o PEO and PEEMU) |  | 2000000 | [6 empty] | PEO | In Collaboration with PEEMU
25 | Completion of Bohol Biodiversity Center Visitor & Manpower Development Center |  | 1500000 | [6 empty] | PEEMU
| Sub-Total |  | 3500000
| TOTAL |  | 3500000
Prepared by:

## PHO (hidden)
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF THE INTERNAL REVENUE ALLOTMENT (IRA)
AS OF THE 1St QUARTER, CY 2018 (as of March 31, 2018)
Province: BOHOL
Office: Provincial Health Office (PHO)
Program or Project |  | Location | Total Cost | Date Started | Target Completion | Project Status |  | No. of Extensions if any | Remarks (Status of implementation)
[6 empty] | % of Completion | Total Cost incurred to Date
SOCIAL SERVICES
26 | Environmental Sanitation Program (Latrine construction for sustainable sanitation to municipalities and island barangays) |  | 1750000 | [7 empty] | PHO
27 | Establishment of 2 additional Animal Bite Treatment Centers |  | 200000 | [6 empty] | Maribojoc Community Hospital - Maribojoc | PHO
| Sub-Total |  | 1950000
| TOTAL |  | 1950000
Prepared by:

## Candijay (hidden)
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF THE INTERNAL REVENUE ALLOTMENT (IRA)
AS OF THE 1St QUARTER, CY 2018 (as of March 31, 2018)
Province: BOHOL
Office: Candijay Community Hospital
Program or Project |  | Location | Total Cost | Date Started | Target Completion | Project Status |  | No. of Extensions if any | Remarks (Status of implementation)
[6 empty] | % of Completion | Total Cost incurred to Date
SOCIAL SERVICES
28 | Installation of Solar Panel for Power Generation at the Candijay Community Hospital |  | 1000000 | [6 empty] | Maribojoc Community Hospital - Maribojoc | Candijay Commnity hospital
| Sub-Total |  | 1000000
| TOTAL |  | 1000000
Prepared by:

## OPSWD (hidden)
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF THE INTERNAL REVENUE ALLOTMENT (IRA)
AS OF THE 1St QUARTER, CY 2018 (as of March 31, 2018)
Province: BOHOL
Office: Office of the Provincial Social Welfare and Development (OPSWD)
Program or Project |  | Location | Total Cost | Date Started | Target Completion | Project Status |  | No. of Extensions if any | Remarks (Status of implementation)
[6 empty] | % of Completion | Total Cost incurred to Date
SOCIAL SERVICES
29 | Construction of the Bohol Youth Home (c/o PEO and OPSWD) |  | 80000000 | [6 empty] | Candijay Community Hospital - Candijay | PEO AND OPSWD
30 | Procurement of relocation site for Indigenous People |  | 1500000 | [7 empty] | OPSWD
31 | Production Center of Assistive Devices for Persons with Disabilities |  | 500000 | [7 empty] | OPSWD
| Sub-Total |  | 82000000
| TOTAL |  | 82000000
Prepared by: