## 2020 complete
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF THE INTERNAL REVENUE ALLOTMENT (IRA)
AS OF THE 1St QUARTER, CY 2021(as of March 31, 2021)
Province: BOHOL
| Program or Project |  |  | Location | Total Cost | Date Started | Target Completion | Project Status |  | No. of Extensions if any | Remarks (Status of implementation)
[8 empty] | % of Completion | Total Cost incurred to Date
GENERAL SERVICES
| 1 | Estimated Loan Amortization for Hospital Modernization Program Phase 1 (Land Bank of the Philippines) |  | Devolved Hospitals | 14678311.12 |  | Dec. 31, 2021 | 20.27% | 2975386.34 |  | Loan Amortization (with interest) for Hospital Modernization (1st phase) due as of March 31, 2021 per schedule
| 2 | Estimated Loan Amortization for Hospital Modernization Program Phase 2 (MDFO) |  | Devolved Hospitals | 5855070 |  | Dec. 31, 2021 | 0% |  |  | Issuance of Certification on Availability of Funds only. Project procurement and deliveries in-progress. Release of proceeds only to be made upon certain % of completion/accomplishment.
| 3 | Estimated Loan Amortization for Hospital Modernization Program Phase 2 (DBP) |  | Devolved Hospitals | 7950000 |  | Dec. 31, 2021 | 0% |  |  | Issuance of Certification on Availability of Funds only. Project procurement and deliveries in-progress. Release of proceeds only to be made upon certain % of completion/accomplishment.
| 4 | Estimated Loan Amortization for Procurement of Heavy Equipment (DBP) |  | GO/PTO | 6540000 |  | Dec. 31, 2021 | 0% |  |  | Issuance of Certification on Availability of Funds only. Project procurement and deliveries in-progress. Release of proceeds only to be made upon certain % of completion/accomplishment.
| 5 | Estimated Loan Amortization for Mrchanization fo Corn/Casava/Fisheries |  | GO/PTO | 3774000 |  | Dec. 31, 2021 | 0% |  |  | Loan application processing in progress.
| 6 | Estimated Loan Amortization for Wter Development Projects (Land Bank of the Philippines) |  | GO/PTO | 30000000 |  | Dec. 31, 2021 | 0% |  |  | Loan application processing in progress.
|  | Sub-Total |  |  | 68797381.12 |  |  |  | 2975386.34
ECONOMIC SERVICES
| 7 | Rehabilitation and Improvement of various Local Roads and Bridges in the Province of Bohol | [9 empty] | PEO
|  | 7.1 | Concreting of San Isidro – Catigbian via Caimbang Road | San Isidro, Catigbian | 10000000 |  | Dec. 31, 2021 |  |  |  | DED on-going
|  | 7.2 | Concreting of Pob. (Catigbian) – Ambuan -Sagasa (Balilihan) | Catigbian, Balilihan | 10000000 |  | Dec. 31, 2021 |  |  |  | DED on-going
|  | 7.3 | Concreting of Candumayao (Catigbian)-Bogtongbod (Clarin, Bohol | Catigbian, Clarin | 15000000 |  | Dec. 31, 2021 |  |  |  | Sched. For Bidding
|  | 7.4 | Concreting of Jct. (LIR) Mahayag – Katipunan Road | San Miguel | 10000000 |  | Dec. 31, 2021 |  |  |  | DED on-going
|  | 7.5 | Concreting of Pob. Inabanga – Lawis Road | Inabanga | 10000000 |  | Dec. 31, 2021 |  |  |  | DED on-going
|  | 7.6 | Concreting of Cambangay (San Miguel) – Soom (Trinidad) Road | San Miguel, Trinidad | 4000000 |  | Dec. 31, 2021 |  |  |  | DED on-going
|  | 7.7 | Concreting of Popoo-Tugas Road, Pres. Carlos P. Garcia | Pres. Carlos P. Garcia | 15000000 |  | Dec. 31, 2021 |  |  |  | DED on-going
|  | 7.8 | Concreting of Ewon Sevilla-Candabong Loboc (Sevilla) Side | Sevilla | 5000000 |  | Dec. 31, 2021 |  |  |  | Sched. For Bidding
|  | 7.9 | Concreting of Cabantian-Cansiwang-Mayuga Road, Guindulman | Guindulman | 20000000 |  | Dec. 31, 2021 |  |  |  | DED on-going
|  | 7.1 | Concreting of Pob.(Sierra Bullones)-Bugsok Road, Sierra Bullones | Sierra Bullones | 3000000 |  | Dec. 31, 2021 |  |  |  | Sched. For Bidding
|  | 7.11 | Concreting of Jct.(Jagna-Sierra Bullones)-Malbog-Calabacita Road, Sierra Bullones | Sierra Bullones | 3000000 |  | Dec. 31, 2021 |  |  |  | DED on-going
|  | 7.12 | Concreting of Roxas Park-Abejilan-Togbongon-Tabuan Road, Garcia-Hernandez | Garcia-Hernandez | 4000000 |  | Dec. 31, 2021 |  |  |  | DED on-going
|  | 7.13 | Concreting of Jct. (TER) Bunga Mar-Kinagbaan-Balili Road, Jagna | Jagna | 25000000 |  | Dec. 31, 2021 |  |  |  | DED on-going
|  | 7.14 | Concreting of Tiguis-Calvario (Lila)-Cambanse-Alegria (Loboc) Road, Loboc | Lila,Loboc | 15000000 |  | Dec. 31, 2021 |  |  |  | DED on-going
|  | 7.15 | Concreting of Bagumbayan-Inaghuban Road, Pilar | Pilar | 15000000 |  | Dec. 31, 2021 |  |  |  | Sched. For Bidding
|  | 7.16 | Concreting of Pob. (Guindulman)-Casbu-Bato Road, Guindulman | Guindulman | 20000000 |  | Dec. 31, 2021 |  |  |  | DED on-going
|  | 7.17 | Concreting of Guadalupe-Monte Video Road, Carmen | Carmen | 4000000 |  | Dec. 31, 2021 |  |  |  | Sched. For Bidding
|  | 7.18 | Concreting of Bilar-Sevilla Road, Bilar | Bilar,Sevilla | 3000000 |  | Dec. 31, 2021 |  |  |  | Sched. For Bidding
|  | 7.19 | Concreting of Can-ipol-Odiong Road, Jagna Road | Jagna | 4000000 |  | Dec. 31, 2021 |  |  |  | DED on-going
|  | 7.2 | Concreting of Guinsularan-Lobogon Road | Duero | 3500000 |  | Dec. 31, 2021 |  |  |  | DED on-going
|  | 7.21 | Construction of Box Culvert (Cross Drainage)-Pob.Carmen to Vallehermoso | Carmen | 1500000 |  | Dec. 31, 2021 |  |  |  | DED on-going
|  | 7.22 | Concreting of Maribojoc-Pagnito-an-Candavid-Tubuan-Basak(Loon) Road | Loon | 10000000 |  | Dec. 31, 2021 |  |  |  | DED on-going
|  | 7.23 | Repair. Rehabilitation and Improvement of Various Local Roads |  | 25000000 |  | Dec. 31, 2021
PEO
| 8 | Provincial Counterpart for the Implementation of the Philippine Rural Development Program (PRDP) |  | Provincewide | 10000000 |  | Dec. 31, 2021 |  |  |  | To be transferred to PRDP Trust Fund as Provincial Counterpart to PRDP Sub-projects
| 9 | Procurement of Machineries to support for rice |  | Provincewide | 4250000 |  | Dec. 31, 2021 |  |  |  | · Docs are for signature @Budget Office - Admin of OPA will make PR after the approval @ Budget Office
50 | 10 | Establishment of Fish Cages in various strategic areas of the province |  | Provincewide | 15200000 |  | Dec. 31, 2021 |  |  |  | · Preparation of Documentary requirements (MOA, Guidelines, POWs) - Identification of 10 POs as beneficiaries of fish cages - POW is yet to be signed but stalled due tolockdown of PGSO due to COVID | PEO
| 11 | Procurement of Ice Making Machine and Cold Storage Facilities |  | Provincewide | 5000000 |  | Dec. 31, 2021 |  |  |  | Preparation of Proposal
| 12 | Establishment of Fish Feed Pellet Line Facility (Including Start up Capital) |  | Provincewide | 12000000 |  | Dec. 31, 2021 |  |  |  | · Preparation of Building Design on going - Occuar inspection of possible area of construction to be done 3rd week of May
| 13 | Procurement of Machineries and Establishment of Structures for ART Cacao |  | Provincewide | 5200000 |  | Dec. 31, 2021 |  |  |  | At Crops Division, lacking list of proposed beneficiaries. The rest of the of the docs are for signature to PA, PPDO & PBO
| 14 | Establishment of Food Dehydrator Facility for Fruits and Vegetables |  | Provincewide | 8800000 |  | Dec. 31, 2021 |  |  |  | Re-aligned to other projects that is given more priority
| 15 | Plant Nursery Enhancement Projects - Machineries and Equipment |  | Provincewide | 2592992.4 |  | Dec. 31, 2021 |  |  |  | On-going preparation of Purchase Request, Specifications of Machineries & Equipment to be procured has to be referred to TWG before the finalization of PR
| 16 | Establishment of the Bohol Innovation Hub |  | Provincewide | 20000000 |  | Dec. 31, 2021
| 17 | Establishment of Two (2) Units Azolla Green Houses |  | PLPF, Bilar | 1000000 |  | Dec. 31, 2021 |  |  |  | Approved Work and Financial Plan
| 18 | Procurement of needed Equipment for Meat Processing |  | Various location in the province | 1000000 |  | Dec. 31, 2021 |  |  |  | Approved Work and Financial Plan
| 19 | Multipurpose Hall/Training Center for Children's Choir |  | Provincewide | 3000000 |  | Dec. 31, 2021 | 0% |  |  | Program of work (POW) preparation still in-progress as of March 31, 2021.
| 20 | Water Desalination Project in Island Barangay |  | Provincewide | 6500000 |  | Dec. 31, 2021 | 0 |  |  | Program of work (POW) still in-progress as of March 31, 2021. Identified project beneficiary is Cuaming Island, Inabanga. Based on estimates of cost computed by PEO, total cost is at P7.5M. A supplemental funding of P1M is included in SB No. 4, series of 2021.
| 21 | Water works Program for Bohol LGU's
|  | 21.1 | Mabini Spring Development(Source 1) | Mabini, Bohol | 30000000 |  | Dec. 31, 2021 | 0% |  |  | Detailed Engineering Design (DED) and POW still in progress as of March 31, 2021.
|  | 21.2 | Dimiao Spring Development | Dimiao, Bohol | 10000000 |  | Dec. 31, 2021 | 0% |  |  | Detailed Engineering Design (DED) and POW still in progress as of March 31, 2021.
| 22 | Establishment of Agri-Fishery Retail Terminal/Market including Equipment (Tagbilaran City, Panglao, Talibon) |  | Tagbilran City, Panglao, Talibon | 15000000 |  | Dec. 31, 2021 | 0% |  |  | POW preparation still in progress. Total amount budgeted to be used in the Agri-Fishery Retail Terminal / Market in the Old Tagbilaran Airport only for the Access to Recreation and Trade convergence initiative.
|  | Sub-Total |  |  | 384542992.4 |  |  |  | 0
SOCIAL SERVICES
| 23 | Rehabilatation of Multi-purpose Building for Persons with Disabilities |  | Tagbilaran City | 2000000 |  | Dec. 31, 2021 |  |  |  | Coordinated with PEO to faclitate necessary documents
| 24 | Food Assistance to Affected Families of COVID-19 |  | Provincewide | 28605707.28 |  | Dec. 31, 2021 |  |  |  | Govedrnor's Office is inchage in the implementation of the program
|  | Sub-Total |  |  | 30605707.28 |  |  |  | 0
|  | TOTAL |  |  | 483946080.8 |  |  |  | 2975386.34
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
| JOSETH J. CELOCIA |  |  |  | JOHN TITUS J. VISTAL |  |  |  | ARTHUR C. YAP
| Provincial Accountant |  |  | Provincial Planning and Development Coordinator |  |  |  |  | Governor

## GO (hidden)
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF THE INTERNAL REVENUE ALLOTMENT (IRA)
AS OF THE 1St QUARTER, CY 2018 (as of March 31, 2018)
Province: BOHOL
Office: Office of the Governor
Program or Project |  | Location | Total Cost | Date Started | Target Completion | Project Status |  | No. of Extensions if any | Remarks (Status of implementation)
[6 empty] | % of Completion | Total Cost incurred to Date
GENERAL SERVICES
1 | Loan Amortization (For Hospital Modernization Program Phase 1) |  | 22475000 | [6 empty] | GO
| Sub-Total |  | 22475000
ECONOMIC SERVICES
12 | Roads Development Program for Bohol LGUs |  | 8000000 | [6 empty] | GO
13 | Waterworks Program for Bohol LGUs |  | 3000000 | [6 empty] | GO
14 | Electrification Program for Bohol LGUs |  | 1500000 | [6 empty] | GO
15 | Various Infrastructure Projects for Bohol LGUs |  | 15000000 | [6 empty] | GO
| Sub-Total |  | 27500000
| TOTAL |  | 49975000
Prepared by:

## BDJ (hidden)
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF THE INTERNAL REVENUE ALLOTMENT (IRA)
AS OF THE 1St QUARTER, CY 2018 (as of March 31, 2018)
Province: BOHOL
Office: Bohol District Jail (BDJ)
Program or Project |  | Location | Total Cost | Date Started | Target Completion | Project Status |  | No. of Extensions if any | Remarks (Status of implementation)
[6 empty] | % of Completion | Total Cost incurred to Date
GENERAL SERVICES
2 | Water Supply Development at the Bohol District Jail (2 Water Tanks) |  | 150000 | [6 empty] | BDJ
3 | Construction of no contact visiting building |  | 1000000 | [6 empty] | BDJ
4 | Construction of 2 cells for mentally-ill inmates |  | 700000 | [6 empty] | BDJ
| Sub-Total |  | 1850000
| TOTAL |  | 1850000
Prepared by:

## PEO (hidden)
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF THE INTERNAL REVENUE ALLOTMENT (IRA)
AS OF THE 1St QUARTER, CY 2018 (as of March 31, 2018)
Province: BOHOL
Office: Provincial Engineer's Office (PEO)
| Program or Project |  |  | Location | Total Cost | Date Started | Target Completion | Project Status |  | No. of Extensions if any | Remarks (Status of implementation)
[8 empty] | % of Completion | Total Cost incurred to Date
ECONOMIC SERVICES
| 5 | Provincial Roads/ Roads Development and Rehabilitation Program | [9 empty] | PEO
|  | 5.1 | Concreting of Cabad Road, Balilihan |  | 5000000 | [6 empty] | PEO | PEO
|  | 5.2 | Concreting of Catigbian - Ambuan - Sagasa Road |  | 5000000 | [6 empty] | PEO | PEO
|  | 5.3 | Concreting of Baclayon - Corella Road |  | 3500000 | [6 empty] | PEO | PEO
|  | 5.4 | Concreting of Cahayag (Tubigon) Causwagan Sur (San Isidro) Road |  | 5000000 | [6 empty] | PEO | PEO
|  | 5.5 | Concreting of Baclayon - Corella Via Tunga Road |  | 2000000 | [6 empty] | PEO | PEO
|  | 5.6 | Concreting of Oneway Traffic, Inabanga |  | 5000000 | [6 empty] | PEO | PEO
|  | 5.7 | Concreting of San Miguel - Tomoc - Jetafe Road (San Miguel Side) |  | 5000000 | [6 empty] | PEO | PEO
|  | 5.8 | Concreting of Casbu Circumferential Road, Guindulman |  | 5000000 | [6 empty] | PEO | PEO
|  | 5.9 | Upgrading of San Isidro, Balilihan Road |  | 3633496.4 | [6 empty] | PEO | PEO
|  | 5.1 | Concreting of Maribojoc-Antequera-via Tinibgan Road |  | 4000000 | [6 empty] | PEO | PEO
|  | 5.11 | Concreting of Guinsularan - Lobogon Road, Duero |  | 4000000 | [6 empty] | PEO | PEO
|  | 5.12 | Concreting of Popoo - Tugas Road CPG |  | 5000000 | [6 empty] | PEO | PEO
|  | 5.13 | Concreting of Batuan - Quezon Road |  | 5000000 | [6 empty] | PEO | PEO
|  | 5.14 | Widening and Upgrading of New Capitol Heights Road |  | 15000000 | [6 empty] | PEO | PEO
|  | 5.15 | Upgrading of Mayacabac-Poblacion, Dauis Road |  | 20000000 | [6 empty] | PEO | PEO
|  | 5.16 | Concreting of Right of Way of the new Cong. Natalio P. Castillo, Sr. Memorial Hospital, Loon |  | 2000000 | [6 empty] | PEO | PEO
|  | 5.17 | Development of Public Access Road along New Provincial Compound, Tagbilaran City |  | 8000000 | [7 empty] | PEO
|  | 5.18 | Concreting of Road at Uptown Housing, Tagbilaran City |  | 5000000 | [7 empty] | PEO
|  | 5.19 | Concreting of Sikatuna-Balilihan Road Via Can-agong/ Poblacion 2 (Sikatuna) |  | 5000000 | [7 empty] | PEO
|  | 5.2 | Construction of Access Road to PGBh Property in Cortes |  | 5000000 | [7 empty] | PEO
| 6 | Lot Acquisition (Right of Way for Hangos Street) Additional (c/o PEO, PLO, PGSO) |  |  | 22500000 | [7 empty] | PEO | In Collaboration with PGSO and PLO
| 7 | Construction of foot bridge at Loreto , Cortes |  |  | 6000000 | [7 empty] | PEO
50 | 8 | Construction of New MQC Building of PEO |  |  | 4000000 | [6 empty] | PEO | PEO
| 9 | Waste Water treatment facility at new Capitol Compound to promote water quality (In Collaboration with PGSO) |  |  | 16500000 | [7 empty] | PEO | In Collaboration with PGSO
| 10 | Construction of the Provincial Manpower Development Center at the New Capitol Heights Compound |  |  | 10000000 | [7 empty] | PEO
| 11 | Road Network Development and other related infrastructure at Bohol Biodiversity Complex, BBC (Phase 1) – Roxas, Bilar, Bohol (c/o PEO and PEEMU) |  |  | 2000000 | [7 empty] | PEO | In Collaboration with PEEMU
|  | Sub-Total |  |  | 178133496.4
SOCIAL SERVICES
| 29 | Construction of the Bohol Youth Home (c/o PEO and OPSWD) |  |  | 80000000 | [6 empty] | Candijay Community Hospital - Candijay | PEO AND OPSWD
|  | Sub-Total |  |  | 80000000
|  | TOTAL |  |  | 258133496.4
Prepared by:

## PGSO (hidden)
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF THE INTERNAL REVENUE ALLOTMENT (IRA)
AS OF THE 1St QUARTER, CY 2018 (as of March 31, 2018)
Province: BOHOL
Office: Provincial General Services Office (PGSO)
Program or Project |  | Location | Total Cost | Date Started | Target Completion | Project Status |  | No. of Extensions if any | Remarks (Status of implementation)
[6 empty] | % of Completion | Total Cost incurred to Date
ECONOMIC SERVICES
6 | Lot Acquisition (Right of Way for Hangos Street) Additional (c/o PEO, PLO, PGSO) |  | 22500000 | [6 empty] | PEO | In Collaboration with PGSO and PLO
9 | Waste Water treatment facility at new Capitol Compound to promote water quality (c/o PEO and PGSO) |  | 16500000 | [6 empty] | PEO | In Collaboration with PGSO
16 | Improvement / Construction / Rehabilitation of PGBh Facilities / Cultural Assets/ Designated Evacuation Center for Public Use to Support Development |  | 16200000 | [6 empty] | PGSO
| TOTAL |  | 55200000
Prepared by:

## PLO (hidden)
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF THE INTERNAL REVENUE ALLOTMENT (IRA)
AS OF THE 1St QUARTER, CY 2018 (as of March 31, 2018)
Province: BOHOL
Office: Provincial Legal Office (PLO)
Program or Project |  | Location | Total Cost | Date Started | Target Completion | Project Status |  | No. of Extensions if any | Remarks (Status of implementation)
[6 empty] | % of Completion | Total Cost incurred to Date
ECONOMIC SERVICES
6 | Lot Acquisition (Right of Way for Hangos Street) Additional (c/o PEO, PLO, PGSO) |  | 22500000 | [6 empty] | PEO | In Collaboration with PGSO and PLO
| TOTAL |  | 22500000
Prepared by:

## OPA (hidden)
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF THE INTERNAL REVENUE ALLOTMENT (IRA)
AS OF THE 1St QUARTER, CY 2018 (as of March 31, 2018)
Province: BOHOL
Office: Office of the Provincial Agriculturist (OPA)
Program or Project |  | Location | Total Cost | Date Started | Target Completion | Project Status |  | No. of Extensions if any | Remarks (Status of implementation)
[6 empty] | % of Completion | Total Cost incurred to Date
ECONOMIC SERVICES
17 | On-farm rice mechanization and postharvest facilities to rainfed areas |  | 5000000 | [6 empty] | OPA
18 | Fish Bagsakan Program - Purchase of 1 Unit Ice Maker |  | 1200000 | [6 empty] | OPA
19 | Fish Bagsakan Program - Construction of Fish Bagsakan Building and Display Racks |  | 2300000 | [6 empty] | OPA
| TOTAL |  | 8500000
Prepared by:

## OPV (hidden)
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF THE INTERNAL REVENUE ALLOTMENT (IRA)
AS OF THE 1St QUARTER, CY 2018 (as of March 31, 2018)
Province: BOHOL
Office: Office of the Provincial Veterinarian (OPV)
Program or Project |  | Location | Total Cost | Date Started | Target Completion | Project Status |  | No. of Extensions if any | Remarks (Status of implementation)
[6 empty] | % of Completion | Total Cost incurred to Date
ECONOMIC SERVICES
21 | Provincial Meat Safety and Control Program (Capital expenditure Component) - Upgrading of Slaughterhouses |  | 2000000 | [6 empty] | OPV
22 | Livestock Production Support Program (Capital expenditure Component) Provision of support to liquid nitrogen plant |  | 1500000 | [6 empty] | OPV
23 | Provincial Livestock and Poultry Farm |  | 2000000 | [6 empty] | OPV
| Sub-Total |  | 5500000
| TOTAL |  | 5500000
Prepared by:

## BEMO (hidden)
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF THE INTERNAL REVENUE ALLOTMENT (IRA)
AS OF THE 1St QUARTER, CY 2018 (as of March 31, 2018)
Province: BOHOL
Office: Bohol Environment Management Office (BEMO)
Program or Project |  | Location | Total Cost | Date Started | Target Completion | Project Status |  | No. of Extensions if any | Remarks (Status of implementation)
[6 empty] | % of Completion | Total Cost incurred to Date
ECONOMIC SERVICES
24 | Construction of native cottages for local and foreign researchers, students, volunteers, and walk-in visitors at the Bohol Biodiversity Center |  | 1000000 | [6 empty] | BEMO
| Sub-Total |  | 1000000
| TOTAL |  | 1000000
Prepared by:

## PEEMU (hidden)
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF THE INTERNAL REVENUE ALLOTMENT (IRA)
AS OF THE 1St QUARTER, CY 2018 (as of March 31, 2018)
Province: BOHOL
Office: Provincail Economic Enterprise Management Unit (PEEMU)
Program or Project |  | Location | Total Cost | Date Started | Target Completion | Project Status |  | No. of Extensions if any | Remarks (Status of implementation)
[6 empty] | % of Completion | Total Cost incurred to Date
ECONOMIC SERVICES
11 | Road Network Development and other related infrastructure at Bohol Biodiversity Complex, BBC (Phase 1) – Roxas, Bilar, Bohol (c/o PEO and PEEMU) |  | 2000000 | [6 empty] | PEO | In Collaboration with PEEMU
25 | Completion of Bohol Biodiversity Center Visitor & Manpower Development Center |  | 1500000 | [6 empty] | PEEMU
| Sub-Total |  | 3500000
| TOTAL |  | 3500000
Prepared by:

## PHO (hidden)
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF THE INTERNAL REVENUE ALLOTMENT (IRA)
AS OF THE 1St QUARTER, CY 2018 (as of March 31, 2018)
Province: BOHOL
Office: Provincial Health Office (PHO)
Program or Project |  | Location | Total Cost | Date Started | Target Completion | Project Status |  | No. of Extensions if any | Remarks (Status of implementation)
[6 empty] | % of Completion | Total Cost incurred to Date
SOCIAL SERVICES
26 | Environmental Sanitation Program (Latrine construction for sustainable sanitation to municipalities and island barangays) |  | 1750000 | [7 empty] | PHO
27 | Establishment of 2 additional Animal Bite Treatment Centers |  | 200000 | [6 empty] | Maribojoc Community Hospital - Maribojoc | PHO
| Sub-Total |  | 1950000
| TOTAL |  | 1950000
Prepared by:

## Candijay (hidden)
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF THE INTERNAL REVENUE ALLOTMENT (IRA)
AS OF THE 1St QUARTER, CY 2018 (as of March 31, 2018)
Province: BOHOL
Office: Candijay Community Hospital
Program or Project |  | Location | Total Cost | Date Started | Target Completion | Project Status |  | No. of Extensions if any | Remarks (Status of implementation)
[6 empty] | % of Completion | Total Cost incurred to Date
SOCIAL SERVICES
28 | Installation of Solar Panel for Power Generation at the Candijay Community Hospital |  | 1000000 | [6 empty] | Maribojoc Community Hospital - Maribojoc | Candijay Commnity hospital
| Sub-Total |  | 1000000
| TOTAL |  | 1000000
Prepared by:

## OPSWD (hidden)
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF THE INTERNAL REVENUE ALLOTMENT (IRA)
AS OF THE 1St QUARTER, CY 2018 (as of March 31, 2018)
Province: BOHOL
Office: Office of the Provincial Social Welfare and Development (OPSWD)
Program or Project |  | Location | Total Cost | Date Started | Target Completion | Project Status |  | No. of Extensions if any | Remarks (Status of implementation)
[6 empty] | % of Completion | Total Cost incurred to Date
SOCIAL SERVICES
29 | Construction of the Bohol Youth Home (c/o PEO and OPSWD) |  | 80000000 | [6 empty] | Candijay Community Hospital - Candijay | PEO AND OPSWD
30 | Procurement of relocation site for Indigenous People |  | 1500000 | [7 empty] | OPSWD
31 | Production Center of Assistive Devices for Persons with Disabilities |  | 500000 | [7 empty] | OPSWD
| Sub-Total |  | 82000000
| TOTAL |  | 82000000
Prepared by: